## Setup before coding
# | Tasks | Effort
01 | Get access to the Brewery | 0
02 | Configure connections Django/SQL database | 2
03 | Test a first "Hello World" printing something from the database for a end-to-end test | 1
04 | Test insert and delete into the database from UI | 1
05 | Have the needed libraries installed | 1

## PBIs - User Stories
# | Short Name | As a… | I want to… | So that… | Definition of Done
US01 | Check filled fields | Finance Analyst | Perform an automatic check (madatory filling) if scanned medical license forms in a specific directory are correctly filled. I also want to know which forms are not OK. | I don't need to loose my time doing it manually and make the process more reliable | -- The user can request The scan to be performed -- As a result for The request, The system display a list of files and their status (Passed or Failed) after checking mandatory fields.
US02 | Check field types | Finance Analyst | Perform an automatic check (data is compatible with the field type) if scanned medical license forms in a specific directory are correctly filled. I also want to know which forms are not OK. | I don't need to loose my time doing it manually and make the process more reliable | -- The user can request The scan to be performed -- As a result for The request, The system display a list of files and their status (Passed or Failed) after checking the field types.
US03 | Check number of signatures | Finance Analyst | Perform an automatic check if the employee signed a scanned medical license form in all the places supposed to be signed | I don't need to loose my time doing it manually and make the process more reliable | -- The user can check how many signature fields are filled out of The total. '-- As a result for The request, The system display a list of the signature field and their status (Passed or Failed).
US04 | Detail form errors | Finance Analyst | Get the details of what's wrong with a form | I can correct it before scanning it again | -- User can select a file to detail the errors found -- For the selected file, the system show all of the scanned fields with current value, expected type, type found, madatory fillinng status and data type status.
US05 | Transcript form | Finance Analyst | Perform a automatic transcription of scanned medical license forms into digital files | I don't need to loose my time doing it manually and make the process more reliable
US06 | Choose directory | Finance Analyst | Be able to choose which directory or specific form should be checked and transcripted | I can have faster feedback
US07 | Table of forms | Finance Analyst | Show the content of the transcipted files disposed in a table format | I have the transcripted data consolidated in one view
US08 | Filter forms | Finance Analyst | Filter the forms that I want to show in a consolidated view by name of the employee, RUT or start date | I can work only on a reduced universe of forms that I interested in
US09 | Export transcriptions to Excel | Finance Analyst | Export the content of the transcipted files in a Excel file | I can flexibly manipulate the data
US10 | Send transcriptions via e-mail | Finance Analyst | Export the content of the transcipted files in a Excel file via Email | I can send it to interested parties that have no access to the system
US11 | Report number of forms | Finance Manager | Show a report of how many reports were correctly and uncorrectly filled in a variable period of time | I can work with my team in order to improve this KPI and perform internal audits before being audited by external parties
US12 | Report by field | Finance Manager | Show a report of how frequently a field in the form is uncorrectly filled or not filled in a variable period of time | I can work with my team and coach the doctors or employees to pay attention to some specific fields that might show higher error frequency
US13 | Help pages | System user | Show a help content for each screen (user interface) of the software | Any new user can read the instructions and use the system even without a formal training
US14 | Compare signatures | Finance Analyst | Perform a automatic check if the employee signature in a scanned medical license form matches a standard employee signature | I don't need to loose my time doing it manually and make the process more reliable
US15 | Auto check running on background | Finance Analyst | Perform a automatic check for for medical license form that I scan using a scanner directly connected to my computer | I have immediate feedback once I scan the forms and don't need to select the directory and request a check manually
US16 | Flexible for other forms | Finance Analyst | Check other type of forms that are not medical leave forms, e.g. reimbursement forms | I can have the same benefits delivered to the original proposed form

## Activities
PBI | Activitiy | Description | Effort [h]
US01 | A01 | Define which fields will be shown to the user
US01 | A02 | Create a mockup in a drawn paper
US01 | A03 | Show mockup to the user and get formal approval
US01 | A04 | Create a mockup with dummy data in Django
US01 | A05 | Show mockup to the user and get formal approval
US01 | A06 | Map fields on the mockup with real dinamic data
US02 | A01 | Show fields with wrong data type, or message in case no mismatch was found.
US02 | A02 | Display message box with mismatches.
US03 | A01 | Check if signature fields are filled
US03 | A02 | Add count signature count column in the view (frontend code)
US03 | A03 | Display signature count (X out of Y)
US04 | A01 | Develop trigger function for showing the detailed view
US04 | A02 | Create a mockup with dummy data in Django for detailed view
US04 | A03 | Show mockup to the user and get formal approval
US04 | A04 | Map fields on the mockup with real dinamic data